## Sheet2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1808891 |  |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-16 | 83:00 | 87:00 | 4 | Add a fallback to the WebApp | So that if the output doesn’t have the correct response, the Web App would still function normally | Finishing the 2nd version of the Web App
Tuesady | 2022-05-17 | 86:00 | 90:00 | 4 | Fix the design on Safari Browser | So that the design is consistent across browser | Finishing the 2nd version of the Web App
Wednesday | 2022-05-18 | 90:00 | 94:00 | 4 | Add ability to override the output | So that the user can simply change the image if the output is not satisfied | Finishing the 2nd version of the Web App
Thursday | 2022-05-19 | 86:00 | 90:00 | 5 | Add “Get Sample Sentence” | So that we can rapidly testing by saving time getting the sentence. | Finishing the 2nd version of the Web App
Friday | 2022-05-20 | 82:00 | 89:00 | 7 | Cleaning the code for the image generation | For better development next time | Finishing the 2nd version of the Web App
|  |  | Total | 24