## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-16 | 10:00 | 14:00 | 4 | Rewrote the training script | Improve the training process by putting parse arguments | Now the training process becomes more flexible by passing arugments into command lines
Tuesday | 2022-05-17 | 8:00 | 14:00 | 6 | Testing the training script | Improve the training process by putting parse arguments | The training process ran well
Wednesday | 2022-05-18 | 10:00 | 14:00 | 4 | Rewrote the testing script | Improve the testing process by putting parse arguments | Now the testing process becomes more flexible by passing arugments into command lines
Thursday | 2022-05-19 | 9:00 | 14:00 | 5 | Testing the test script | Improve the test process by putting parse arguments | The test process ran well. A single command line is able to test the model
Friday | 2022-05-20 | 9:00 | 15:00 | 6 | Introducting delpoyment script | instead of typing the commands line by line, a script will do the work when model is ready to deploy | A single command line is able to deploy the model
|  |  | Total | 25