## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-24 | 9:00 | 14:00 | 5 | Implement logging system in training | Sometime is hard to debug without a logging system | Now logs are saved in to train.log
Tuesday | 2022-05-25 | 9:00 | 14:00 | 5 | Implement logging system in testing | Sometime is hard to debug without a logging system | Now logs are saved in to test.log
Wednesday | 2022-05-26 | 11:00 | 14:00 | 3 | Integrate all the training script, test script | Optimization for auto detect when new dataset is avaliable | Now the it will start training process when there is a new dataset avaliable
Thursday | 2022-05-27 | 11:00 | 14:00 | 3 | Integrate all the training script, test script | Auto test and delpoyment after the training process is finished | Now the it will start delpoyment when test and train are done.
Friday | 2022-05-28 | 9:00 | 17:00 | 8 | Final test on the automataion process | Optimization for machine learning | Expected result, process from training to deployment ran well
|  |  | Total | 24