## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-31 | 9:00 | 14:00 | 5 | Some final adjustment on the model | Improve model performance | Continue to improve the model
Tuesday | 2022-06-01 | 9:00 | 14:00 | 5 | Some final adjustment on the model | Improve model performance | The model now is running faster than the last one
Wednesday | 2022-06-02 | 11:00 | 14:00 | 3 | Investigate why the loading time of the model is so slow | Improve model performance | When the model is running, the docker image need to download the pretrained model
Thursday | 2022-06-03 | 11:00 | 14:00 | 3 | Fix the loading time for the model | Improve model performance | Now the it will start delpoyment when test and train are done.
Friday | 2022-06-04 | 9:00 | 17:00 | 8 | Running all the scripts to test | Final checking on the model | The model seems to work well
|  |  | Total | 24