## Sheet2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1805827 |  | Constracted a brief framework and schedule of the following processes. | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 07/03/2020 | 11:00 | 14:00 | 3 | Attended the workshop and had a disscusion with one of the team memebers. | Sharing each other thoughts and ideas of the project which will costruct the foundation of the project. | Have a formal group meeting and client meeting as soon as possible.
Tuesday | 08/03/2021 | 15:00 | 18:00 | 3 | Attended the workshop and had emails with our client Thomas. | Having the client meeting scheduled, meaning the designing processes can be started soon. | Have a formal group meeting and prepare the meeting aganda for tomorrow client meeting.
Tuesday | 08/03/2022 | 20:00 | 10:00 | 2 | Had a formal group meeting. | Having preparation before the client meeting, will make the sure the client meeting go as planed. | Questions and agenda prepared, the whole team had deeper underatanding and analysis of the project.
Wednesday | 09/03/2023 | 14:00 | 18:00 | 4 | Had the first client meeting with our client Thomas. | Had comfirmed more information about the project with our client. | Collect relative description data and image data, start constructing the frame.
Thursday | 05/03/2024 | 21:00 | 23:00 | 2 | Analyzed the description data found by Kelvin. | The description data found by Kelvin can be used for the description analysis deep learning section. | Start constructing the frame of the description analysis deep learning section.
Thursday | 05/03/2024 | 14:00 | 18:00 | 4 | Had a discussion with Alan about the image generation data. | Since the description data found by Kelvin can only be used for the description analysis deep learning section, the project still needs the image data for the deep learning image generator. section. | Collect relative image data, and parse the description data.
Friday | 05/03/2025 | 14:00 | 17:00 | 3 | Had a disscusion with Alan about the working and following week schedules. | Shared each other thoughts and ideas of the project and the assignemnts, planed part of the schedule for the mext client meeting and pitch.Shared each other thoughts and ideas of the project and the assignments, planned part of the schedule for the next client meeting and pitch. | Start preparing the Pitch presentstion.
Saturday | 05/03/2026 | 14:00 | 18:00 | 4 | Collecting image photo data, and preparing meeting agenda for the next week. | Image data that will be used for the deep learning image generator section. | Found some image data. Next step, analysis and modify both two sets of data, only keeping the most suitable data for the project.
|  |  | Total | 25