## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-21 | 10:00 | 14:00 | 4 | Regular meeting with client | Making sure everyone is on the same page | Suggest to create a generator for data
Tuesday | 2022-03-22 | 11:00 | 16:00 | 5 | Reseach on generator | As we want to develop for the generator | The generator is not very easy to implement. And it might take time
Wednesday | 2022-03-23 | 12:00 | 16:00 | 4 | Continue on reseach, discussion with team for the pitch presentation | I need to discuss with teammates about the generator and pitch presentation. | We finish the draft of the pitch. We want to get our data from labelling.
Thursday | 2022-03-24 | 9:00 | 17:00 | 8 | Develop labelling application | we need a efficient way to label our data | Implemented in node js
Friday | 2022-03-25 | 9:00 | 18:00 | 9 | Continue on development | adding view image to speed up labelling process | Implemented in node js
Saturday | 2022-03-26 | 8:00 | 20:00 | 12 | Continue on development | Some minor bug fix and testing | the application is online. We are starting to label the data
|  |  | Total | 42