## Sheet2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1805827 |  |  | Week starting:
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-28 | 10:00 | 18:00 | 8 | Had the client meeting with Thomas, showed Thomas the current working processes. Comfirmed the details of bulding a generater. Attended the workshop. Builed the demo generator. | The generator can provide more various data, the more suitable data we have, the more accurate that our machine learning can be. | Prepare the video of the pitch presentation.
Tuesady | 2022-03-29 | 11:00 | 17:00 | 6 | Improved the generator. Recored the draft pitch presentation video. | The generator need more variables to provide more various data, the more suitable data we have, the more accurate that our machine learning can be. Pitch presentation is part of the assignments, it is also a summary of the project's purpose, requirement and operations. | Modify and edit the draft pitch presentation video, and submit.
Wednesday | 2022-03-30 | 12:00 | 18:00 | 6 | Modified and improved the generator. | The generator need more variables to provide more various data, the more suitable data we have, the more accurate that our machine learning can be. | Have a meeting to confirmed the style that we will be used for our project.
Thursday | 2022-03-31 | 16:00 | 18:00 | 2 | Had a discussion with Alan for more modification on the data. | Different people have different opinions about the data. The generator need more variables to provide more various data, the more suitable data we have, the more accurate that our machine learning can be. | Have a meeting to confirmed the style that we will be used for our project.
Saturday | 2022-04-02 | 13:00 | 17:00 | 4 | Modified and improved the generator. | The generator need more variables to provide more various data, the more suitable data we have, the more accurate that our machine learning can be. The output and variables need to be comfirmed by the team. | Seek for opinions about the generated data from the generator.
|  |  | Total | 26