## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-28 | 10:00 | 14:00 | 4 | Regular meeting with client and code review | Report the performance on the model | Our next action is optimziing the model
Tuesday | 2022-03-29 | 13:00 | 17:00 | 4 | Code review on data preprocessing | The model seems not working well, we need to investigate if bugs exist. | Remove one hot vector embedding to simplify the data preprocessing, acurracy improve 7 %
Wednesday | 2022-03-30 | 11:00 | 16:00 | 5 | Improve data preprocessing and data checking | The model accuracy is around 47% which is not good enough. Continue work on the model | Bug fixing on the data preprocessing. Report to Collin there also some bugs in data.
Thursday | 2022-03-31 | 11:00 | 16:00 | 5 | Study on the Adam optimization | Continue work on the model on accraucy improment | Trying different learning rate on the model. Accuracy jumps to 99.6%
Friday | 2022-04-01 | 9:00 | 16:00 | 7 | Build tensorboard for hyper paramemeter tunning | One way to optimize the model is to tune the hyper paramemters | learning rate of 0.03 with the batch size 128 archives the. Best result
Saturday | 2022-04-02 | 9:00 | 13:00 | 2 | Virtualize the model | Building graphs to show the performance for the next client meeting | Grpahs are built in html format for easy presenetation
|  |  | Total | 27