## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-04 | 10:00 | 14:00 | 4 | Regular meeting with client and code review | Report the performance on the model | Our next action is optimziing the model
Tuesday | 2022-04-05 | 13:00 | 19:00 | 6 | Change the model, prepare for difficult dataset | The model seems not working well, optimze the model for complex data pipline | Ask colin for the dataset
Wednesday | 2022-04-06 | 9:00 | 16:00 | 7 | Implement the model in Google Colab | Google colab offer free machine learning platorm | Testing machine learning in google colab
Thursday | 2022-04-07 | 11:00 | 16:00 | 5 | Optimize GPU Google Colab | Investigate how to use GPU in google colab | Train model
Friday | 2022-04-08 | 9:00 | 16:00 | 7 | Setting up tensorboard for training | Tensor records the training process | Start training
Saturday | 2022-04-09 | 9:00 | 13:00 | 4 | Train the model | Model is training in Google Colab | Result is 99.7%
|  |  | Total | 33