## Sheet2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1808891 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-09 | 35:00 | 39:00 | 4 | Building the database on Airtable | Hosting all 3D files online so that the Web App can pull from | Finishing the 1st version of the Web App
Tuesady | 2022-05-10 | 38:00 | 42:00 | 4 | Building the Web App UI on Webflow | A Web App that is separated from the database to maintain connection and server load | Finishing the 1st version of the Web App
Wednesday | 2022-05-11 | 42:00 | 46:00 | 4 | Continue to add all necessary 3D models that matches with the base human model | So that all of the category such as Top, Bottom, Shoes, etc can fit within the base human model | Upload these 3D models to Airtable
Thursday | 2022-05-12 | 38:00 | 42:00 | 5 | Redesigning the Web App UI for better presentation | So that the user will be able to see the model better and know which category is affecting which | Finishing the 1st version of the Web App
Friday | 2022-05-13 | 34:00 | 41:00 | 7 | Connecting Kelvin’s API to the WebApp | So that the web app can see the text to the Machine Learning Model and receive the output which can then be used for image generation | Finishing the 1st version of the Web App
|  |  | Total | 24