## Week 2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | a1829445 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-09 | 9:00 | 14:00 | 5 | Studying on docker | Part of the depoyments | Writing scripts to produce
Tuesday | 2022-05-10 | 9:00 | 14:00 | 5 | Production of container | Part of the depoyments | Container produced
Wednesday | 2022-05-11 | 11:00 | 14:00 | 3 | Testing performance of container | Part of the depoyments | Made api request to the model, perofmance is not good
Thursday | 2022-05-12 | 11:00 | 14:00 | 3 | Research on other deployment method | Part of the depoyments | Flask web application might be good
Friday | 2022-05-13 | 9:00 | 17:00 | 8 | Implement flask application | Part of the depoyments | Now we can make a api request though a flask web application in python
Saturday | 2022-05-15 | 9:00 | 10:00 | 1 | Production and test the container | Part of the depoyments | Perofmance is good.
|  |  | Total | 25